## Project Plan
Project Plan - Project Name Goes Here
| Task Number | WBS Number | Task Description | Predecessor | Effort (delay) | Who does it | Start | End
| 1 | 1 | Install New PCs
| 2 | 1.1 | Choose new PCs |  | 2 | John | 2025-06-02 | 2025-06-03
| 3 | 1.2 | Select Software |  | 2 | John | 2025-06-04 | 2025-06-05
| 4 | 1.3 | Order PCs and Software | 1.1, 1.2 | 1 | John | 2025-06-06 | 2025-06-06
| 5 | 1.4 | Wait for PCs to be delivered | 1.3 | 20 |  | 2025-06-07 | 2025-07-03
| 6 | 1.5 | Install Software on PCs | 1.4 | 13 | Jane | 2025-07-04 | 2025-07-22
| 7 | 1.6 | Install Configured PCs | 1.5 | 17 | Jane | 2025-07-23 | 2025-08-14
Milestone 1: PCs ready and configured for all users
| 8 | 2
| 9 | 2.1
| 10 | 2.2
| 11 | 2.3
Milestone 2: Description Goes Here
| 12 | 2.4
| 13 | 3
| 14 | 3.1
| 15 | 3.3
Milestone 3: Description Goes Here
| 16 |  | Project Contingency |  | 22 | Project Manager | 2023-04-01 | 2023-05-01
This project management template follows the guidelines from Richard Newton’s ‘Project Management Step by Step: How to Plan and Manage a Highly Successful Project’. This project management template follows the guidelines from Richard Newton’s ‘Project Management Step by Step: How to Plan and Manage a Highly Successful Project’. This project management template follows the guidelines from Richard Newton’s ‘Project Management Step by Step: How to Plan and Manage a Highly Successful Project’.
Formulas:
End = WORKDAY([Start],[Effort (delay)]-1)
Start = [End, row above]+1